## Sheet1
C.O.O.L.S.
ACTIVITY |  | Oct. 22nd |  |  |  | Oct. 26th | [6 empty] | Nov. 2nd | [6 empty] | Nov. 9th | [6 empty] | Nov. 16th | [6 empty] | Nov. 23rd | [6 empty] | Nov. 30th | [6 empty] | Dec. 7th | [6 empty] | Dec 14th.
|  | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Prototype Smart Fridge
Finalisation of Web server | Daniel
Testing | bar: Oct. 22nd T to Oct. 22nd F; Oct. 26th M to Oct. 26th W
Webcam Scanning | Alex
Recognised by Pi | bar: Oct. 22nd T to Oct. 22nd F
Implementation | bar: Oct. 26th M to Oct. 26th F; Nov. 2nd M to Nov. 2nd F; Nov. 9th M to Nov. 9th T
Recognising the barcode | bar: Nov. 9th W to Nov. 9th F; Nov. 16th M to Nov. 16th T
Getting products from barcode | bar: Nov. 16th M to Nov. 16th W
Open door sensor | Andrew
Design and hardware connection | bar: Oct. 22nd T to Oct. 22nd F
Implementation | bar: Oct. 26th M to Oct. 26th F; Nov. 2nd M to Nov. 2nd T
Testing | bar: Nov. 2nd T to Nov. 2nd T
Touchscreen | Scott & Daniel
Create user Interface design | bar: Oct. 22nd T to Oct. 22nd F; Oct. 26th M to Oct. 26th T
Implementation | bar: Oct. 26th W to Oct. 26th F; Nov. 2nd M to Nov. 2nd T
Testing | bar: Nov. 2nd F; Nov. 9th M to Nov. 9th T
Finalised LED temperature | Paul
Planning final temperature thresholds | bar: Oct. 22nd T to Oct. 22nd F
Implementation | bar: Oct. 26th M to Oct. 26th F
Testing | bar: Nov. 2nd M to Nov. 2nd W
Finalised Smart Fridge
Attaching of prototype components to fridge
Layout and placement | bar: Nov. 16th M to Nov. 16th W
Wiring and connection of components | bar: Nov. 16th T to Nov. 16th F; Nov. 23rd M to Nov. 23rd F; Nov. 30th M to Nov. 30th W
Testing of pretty smart fridge | bar: Nov. 30th M to Nov. 30th F
Extras? | bar: Dec. 7th M to Dec. 7th F; Dec 14th. M to Dec 14th. F